## Sheet1
DATE | WORK DESCR. | CONTENT & INPUTS | UPDATES | Team Remarks
2021-01-10 | Design started (only for home page & Blog)
2021-01-12 | Home page designed & mailed | Got 3D character ref. on email by Jenis
2021-01-15 |  |  | Sent revised home page design, blog design & navigation options
2021-01-16 |  |  | Revised Home page layout with 3 color options
2021-01-18 |  | Selcted baige BG color option with dark green footer | Revised Home page with 4 color options
Sent options for navigation menu animations
| Sent final layout with color theme, navigation animation & blog layout | Approved layout by Jenis
2021-01-19 | Development started
2021-01-22 |  | Got content for event (1 mockup event) |  | New Layout designed for event
2021-01-30 | Home page goes live on demo URL
2021-02-02 |  | Got partial content for About Us section
2021-02-03 |  | Got content for Programs section, Feedbacks
|  | 1. Bubbles animation to be slowed down. Bubbles can also zoom in with the website instead of a direct bubble appearing. | Done (Note: Zooming in bubbles not in scope for dynamic content) | Only for BG blobs
|  | 2. Flow is happiness bubble has a straight line in bottom and top when it expands | Done
|  | 3. Home, about etc sections looks good with red blob. Can change how the buttons looks when mouse is hovered (right now they become back and underlined), can be done something else | Done
|  | 4. Current events, Feedback and our gallery - heading can be improved + 'See All' and 'Details' button can remove '<<', any way to enhance these two buttons? | Done
|  | 5. 'Send message' and 'subscribe' button color to be the same as footer color | Done
|  | 6. Reach us - change the msg to: Tap into the flow with us by sending us a message. Our team will reach out to you shortly. | Done
|  | 6.Also, in blogs please add a comments section. | Not in scope | Basic blog doesn't include comments & categories
2021-02-04 |  | Got 1 blog write up with SEO tags & category. | Images selected & uploaded (Note: Only static (predefined) categories wil be give)
Got gallery images content
2021-02-05 |  | 1. Below I am flow! Free to learn our way: It all began with a question, ‘What was something that was not a part of my education, but I wish it was!’ | Done
|  | 2. Flow is happiness bubble: Flow began with an idea of a world with a vision of kinder kids, emotionally learned beings, socially inclusive students with a sense of community spirit, humane communication, happier folks, facilitating We(s) in the world of I(s) and of people in touch with their inner world with all of its landscapes, flowers, dreams and power. With research of over 1 year, we have wrapped it all up in our program,' Free to Learn Our Way' | Done
Others:
|  | Also, please could you remove the stars rating in feedback. Also, 'Send message' and 'Subscribe' button color isn't changed. | Done
2021-02-06 |  | Got content for 1 past event | Added in events section
|  | 1. Read more can be removed | Done
|  | 2. The graphic of the girl seems to be blurred. Also the text seems below her, was it meant to be next to her? | Done
|  | 3. The text seems to be just placed, can add more design elements in places like Flow began with a question and all the questions. | Done
|  | 4. Can add some design element in the main text as well. | Done
2021-02-08 |  | Got video testimonial (youtube link) for gallery
|  | Hope changes are made and programs section is on its way. One thing that is misssed it- " Flow is...Happiness. What we crave, carves us." has to be removed. if we need a heading, we can change it to simply "Flow is.... here" (here as in arrived, launched) | Done
2021-02-10 |  | Page-1
|  | Clicking on the FLOW logo should bring back the user to the homepage. | Done
Side Blob is disfigured- Check.
|  | Correction- WOLF= Workshops on learning and facilitation | Done
Page- 2
|  | Add a pause after Flow is, on the second page (Flow is… here). | Done
|  | Add the video sent in the gallery section. | Done
No changes made in the About page- Add graphics
|  | Change the heading from PROGRAMS to Free to learn our way(FLOW). Do the same in the teacher’s training program- Workshops on Learning and Facilitation. | Done
|  | The programs page should start directly with the overview section. Remove read more from there. | Done
Graphical elements missing-
|  | Add graphics to this page. It’s just text. Need more creativity. | Character will be changed.
- self, school and students section.
- AIR should ideally be through graphical blobs and landmarks.
-Milestone for (How to collaborate?) section as reference was given but just text was put
- more ideas from your end to add graphics instead of text!!
Contact-
|  | Reach us should come above instead of the address and phone numbers as address and others things are already mentioned down below. | Done
Events-
|  | Add graphical element instead of the yellow box, when the event is opened. Should look more attractive and interesting to the user. | Done
|  | Yellow blob in the REACH US section matches with the event blob. Make it look different, so as not to confuse. | Done
Bubble graphics not fluidic in some areas.
|  | Read more instead of Know more. | Done
|  | (Menu> Programs)Dropdown menu inside the program’s sections misses graphical elements- (Looks plain in white box) | Done
2021-02-13 |  | Send idea (XD png file) for "FLOW" word representation like logo | Done | Give pre-defined categories in blog. No comments section will be given. Events section cannot be categorised to "past" & "current" events. Site cannot be made Live without SALES clearance.
Bullet points representation to be changed. Ref will be sent by Jenis
Color of White blob in the headings to be changed
Shape of blobs for AIR to be changed
Increase size & weight of overview content in both programs
White background color to be changed in timeline